## Product Backlog
Product Backlog
Product Owner:
ID | Stories | Points | Sprint Backlog No. | Done
1 | - Fixed: mMainAddIn tabs layout, column width | 3 |  | 1
2 | - Fixed: mMainAppMap tabs layout, column width | 3 |  | 1
3 | - Fixed: mMainExtTools tabs layout, column width | 3 |  | 1
4 | - Fixed: mMainSol tabs layout, column width | 3 |  | 1
5 | - Fixed: mMainLS tabs layout, column width | 3 |  | 1
6 | - Fixed: cCalc007Kepler mMain link | 3 |  | 1
7 | - Fixed: cCalc008Time mMain link | 3 |  | 1
8 | - Fixed: cCalc009TScope mMain link | 3 |  | 1
9 | - Fixed: cCalc010EquaCalc mMain link | 3 |  | 1
10 | - Fixed: removed redundant MathJax folder | 3 |  | 1
11 | - Fixed: mMain column width | 3 |  | 1
12 | - Fixed: mMainEqu format | 3 |  | 1
13 | - Fixed: remove old cInfo Equation list | 3 |  | 1
14 | - Fixed: Moved all Solar data to cDataSets/Solar | 3 | 2
15 | - Fixed: mMenuMainDataSet.html for above move | 3 | 2
16 | - Fixed: cData010Sun.html mMain button | 3 | 2
17 | - Added: cData010Sun.html new tab for all Solar Data | 3 | 2
18 | - Added: February 2017 Sunspot data update from RecentIndices.txt | 3 |  | 3
19 | - Added: Allocated To column Added To sprint sheets | 3 |  | 3
| ID Cross Check Sprints |  | Points Cross Check Sprints
190 | 190 | 57 | 57
ID numbers in column 'A' should = ID numbers total for all sprints except 'Last', to ensure all Product Backlog items not yet released are allocated to a 'Sprint'.
‘Product Owner’ is responsible for backlog and story priority, accepts and rejects work, helps define ‘done’

## Sprint 3
| Sprint Backlog Next |  | Scrum Task Board
ID | Stories | Points | To Do | Allocated To | In Progress | Testing | Done
--------------------------------------------------------------------------
| CHANGES FOR ASTROLAB DEVELOPMENT RELEASE v1.0203_20170307 |  | <-- +- the version number as items are added / taken off this backlog
--------------------------------------------------------------------------
This release brings a few new features and fixes:
18 | - Added: February 2017 Sunspot data update from RecentIndices.txt | 3 |  |  |  |  | 1
19 | - Added: Allocated To column Added To sprint sheets | 3 |  |  |  |  | 1
37 |  | 6
When complete the above highlighted text is sorted and can be copied direct to a Readme.txt file for the release
Release Version number above increments by number of changes since last release.
Sprints are 'development iterations' prepared for in 'Iteration 0'

## Sprint 2
| Sprint Backlog Latest |  | Scrum Task Board
ID | Stories | Points | To Do | Allocated To | In Progress | Testing | Done
--------------------------------------------------------------------------
| CHANGES FOR ASTROLAB DEVELOPMENT RELEASE v1.0202_20170304 |  | <-- +- the version number as items are added / taken off this backlog
--------------------------------------------------------------------------
This release brings a few new features and fixes:
14 | - Fixed: Moved all Solar data to cDataSets/Solar | 3 |  |  |  | 1
15 | - Fixed: mMenuMainDataSet.html for above move | 3 |  |  |  | 1
16 | - Fixed: cData010Sun.html mMain button | 3 |  |  |  | 1
17 | - Added: cData010Sun.html new tab for all Solar Data | 3 |  |  |  | 1
62 |  | 12
When complete the above highlighted text is sorted and can be copied direct to a Readme.txt file for the release
Release Version number above increments by number of changes since last release.
Sprints are 'development iterations' prepared for in 'Iteration 0'

## Sprint 1
| Sprint Backlog 1 |  | Scrum Task Board
| Stories | Points | To Do | Allocated To | In Progress | Testing | Done
--------------------------------------------------------------------------
| CHANGES FOR ASTROLAB DEVELOPMENT RELEASE v1.0024_20160519 |  | <-- +- the version number as items are added / taken off this backlog
--------------------------------------------------------------------------
This release brings a few new features and fixes:
1 | - Fixed: mMainAddIn tabs layout, column width | 3 |  |  |  |  | 1. Code updated
2 | - Fixed: mMainAppMap tabs layout, column width | 3 |  |  |  |  | 1. Code updated
3 | - Fixed: mMainExtTools tabs layout, column width | 3 |  |  |  |  | 1. Code updated
4 | - Fixed: mMainSol tabs layout, column width | 3 |  |  |  |  | 1. Code updated
5 | - Fixed: mMainLS tabs layout, column width | 3 |  |  |  |  | 1. Code updated
6 | - Fixed: cCalc007Kepler mMain link | 3 |  |  |  |  | 1. Code updated
7 | - Fixed: cCalc008Time mMain link | 3 |  |  |  |  | 1. Code updated
8 | - Fixed: cCalc009TScope mMain link | 3 |  |  |  |  | 1. Code updated
9 | - Fixed: cCalc010EquaCalc mMain link | 3 |  |  |  |  | 1. Code updated
10 | - Fixed: removed redundant MathJax folder | 3 |  |  |  |  | 1. Code updated
11 | - Fixed: mMain column width | 3 |  |  |  |  | 1. Code updated
12 | - Fixed: mMainEqu format | 3 |  |  |  |  | 1. Code updated
13 | - Fixed: remove old cInfo Equation list | 3 |  |  |  |  | 1. Code updated
91 |  | 39
When complete the above highlighted text is sorted and can be copied direct to a Readme.txt file for the release
Release Version number above increments by number of changes since last release.
Sprints are 'development iterations' prepared for in 'Iteration 0'

## Iteration 0
Iteration 0 |  | Scrum Task Board
Stories | Points | To Do | In Progress | Done
Hardware | 3 |  |  | 1. iMac
Software | 3 |  |  | 1. Dreamweaver
6
Stories' are just items required for Sprint / Iteration 1 to suceed. In this case just the hardware and software to develop the application.

## Burnup
Burnup Chart
Product Backlog Total Points |  | 60
Last | 60 | 0
Latest | 0 | 0
Next | 0 | 0